## Prodution
Task Id | Description | Status | Completed On | dev's Comments | Aravind's Comments | Sivaji Comments | ITSupport's Comments
SQL Server Development Edition | Highly recommend to use SQL Server Development Edition for development purpose and currently team is using expression edition for this. SQL server development edition is free licensed from 2016 by Microsoft | NA |  | Pending from IT Support team,Prabhkar is doing followup | Please make sure we have authentic source from Microsoft confirming Developer Edition is free for our type of use | Yes, I’ve verified the same on MS site and I see the SQL Server 2016 onwards it’s free. | Supports only for windows 6
SQL Service Accounts: | Currently system uses SA login (super user) for all applications and it is not highly recommeded and security concerns.Recommending to create new sql accounts for each and every application. Plan: application team need to share application details to create service accounts in sql server and Update connection strings by application support team | In progress | June-04-2018 | Plan of Action: 1.3 sql accounts identified and created for different apps. 2.working on identified connection to be updated 3.Need to put a plan for apps connection pool changes 4.disabled SA accounts after step 2 | Please do this.
Temp db Configuration | Need to configure multiple tempdb database files to avoid drive contention | Not started |  | Will take up during next sql patching time | Please do this.
Security Group for server access |  | Mail sent on 25 june 2018 |  | Mail initiated to IT SUPPORT
Windows Patching |  | Mail sent on 25 june 2018 |  | Mail initiated to IT SUPPORT
Segregate Application and database servers: | Currently multiple applications and database server are running in same server. This is not standard approach.Need to plan for move database server to dedicated server with proper computing resources | Not started |  | Need to plan | Please evaluate the business need Vs OS, SQLServer licensing and h/w costs and take a call.
Standard Maintance Schedule for Windows and SQL | Scheduler for SQL Patching & windows patching- | Not started
SQL Patching | Server is running with SQL Server 2014 with Service Patch1 only. Need to apply Service Patch2 and latest cummulative update (CU11) Plan: 1) Need 2 hours maintenance window for this cluster SQL Server 2) Run full backups all user databases and system databases. 3) Need to Verify application functionality | DONE | JUNE-09-2018 | New patch CU12 for SP2 SQL 14 is released from 18June2018.patch is planned on july 2018. 1.Windowd patch to be applied prior to this patch update. 2.sql patch update on dev server 3.Patch will be updated on Prod after 1 week from step2. | Please evaluate the impacts on application and have a mitigation plan (like downgrade plan) for unknown issue that may crop up.
Recovery Model | The following databases are simple recovery model and need to update full recovery model since databases are in production. RMS_PRODUCTION tally_12042017 RADSpaAuditDB RADSpaBRMSDB RADSpaCollaborationDB RADSpaFAXDB RADSpaHL7DB RADSpaNotificationDB RADSpaPACSRouteDB RADSpaPACSStoreDB RADSpaRISRadiologyDB RADSpaSysMonitor RADSpaTenantDB RADSpaUserSchedulerDB tally_25052017 V_15012018 powerlink | DONE | June-27-2018 | 1.Un-used db's dropped with final backup 2.updated recovery model from "Simple" to "FULL". | We need to consult iPlatina and RADSPA for all the above database related changes. Couple of them are our test dbs like tally*.
Database Backup: | Need to update database backup method and currently full backups are configured in nightly with full backups only. Need to configure transaction log backups with hourly basis to improve database recovery | Done | June-21-2018 | 1.Recovery model for all dbs created. 2.Nightly Full backup and hourly transactional log backups are implemented with 7 days retention period. 3.Need to move to NAS drive-Pending 4.need to verify backup clean up running fine on Monday(july -1 -2018) | Please do this and also put in place backup management process and fully automate it. Disk space requirements need to be evaluated.Please identify and setup maintenance tasks as required like Rebuild Index, Reorganize index etc….
Memory config | Configure Max memory and minimum for sql server for better performance. | Done | June-23-2018 | max memory :12gb min memory:2 gb to sql 12 gb available for OS & Apps | Since appserver and dbserver share the same resources, please find resource needs for both and assign memory as needed so that appserver performance is not impacted.
Lock Pages(LPCM) | Enable lock pages and perform volume maintenance privilege to SQL Server service account. | DONE | June-19-2018 | LPCM & Perform volumn tasks for sql server account is enabled ,changes will effect in next server reboot. | Please do this.
Auto Close | Auto close Database property is enabled for all databases and it not recommended for production databases | Done | June-1-2018 |  | Please do this.
Standard maintenance plans | a.Full backup daily 12 am b.transactional log back up -hourly c. Rebuild and Re-organise Index optimization-Weekly d.Integrity Check db daily e.Enable standard trace flags | Done | June-20-2018 | Completed all jobs
Database Email for notification |  | Done | June-18-2018 | DB mail configured to received notifications for failed jobs.
Severity Alerts |  | Done | June-22-2018 | Severity alerts 16-25 are configured

## Dev Tasks
Task Id | Description | Status | Completed On | dev's Comments
1 | Identify Heap tables | In progress | ETA is July -31-2018 | 1.Identify Heap tables for large records tables.(June-25-2018). 2. Shared Heap tables to Bala raj.
2 | Identify Long Running Queries | Done | June-22-2018 | Sp(sp_WhoisActive) Is created on UAT & PROD 2.use DBA_TOOLS to view "Sp_WhoisActive" Procedure.
| DeadLocks | Done | June-27-2018 | Enable trace log 1222 globally on service restart will sql deadlocks information to error log to analyse further. 2.To view dead lock info, use 'xp_readerrorlog' command.

## UAT
Task Id | Description | Status | Completed On | Dev's Comments | Aravind's Comments | Sivaji Comments | ITSupport's Comments
SQL Server Development Edition | Highly recommend to use SQL Server Development Edition for development purpose and currently team is using expression edition for this. SQL server development edition is free licensed from 2016 by Microsoft |  |  |  | Please make sure we have authentic source from Microsoft confirming Developer Edition is free for our type of use | Yes, I’ve verified the same on MS site and I see the SQL Server 2016 onwards it’s free.
SQL Patching | Server is running with SQL Server 2014 with Service Patch1 only. Need to apply Service Patch2 and latest cummulative update (CU11) Plan: 1) Need 2 hours maintenance window for this cluster SQL Server 2) Run full backups all user databases and system databases. 3) Need to Verify application functionality | Done | June-05-2018 |  | Please evaluate the impacts on application and have a mitigation plan (like downgrade plan) for unknown issue that may crop up. | Below are the licenses we have. Plesae evaluate if it’s ok to use Server Patch2 with below licensing entitlement:
SQL Service Accounts: | Currently system uses SA login (super user) for all applications and it is not highly recommeded and security concerns.Recommending to create new sql accounts for each and every application. Plan: application team need to share application details to create service accounts in sql server and Update connection strings by application support team | Not needed |  |  | Please do this.
Segregate Application and database servers: | Currently multiple applications and database server are running in same server. This is not standard approach.Need to plan for move database server to dedicated server with proper computing resources |  |  |  | Please evaluate the business need Vs OS, SQLServer licensing and h/w costs and take a call.
Full recovery model | The UAT databases are simple recovery model and need to update full recovery model | DONE only for required dbs | June-11-2018 |  | We need to consult iPlatina and RADSPA for all the above database related changes. Couple of them are our test dbs like tally*.
Database Backup: Transaction Log backups | Need to update database backup method and currently full backups are configured in nightly with full backups only. Need to configure transaction log backups with hourly basis to improve database recovery | Not needed for all dbs | June-11-2018 |  | Please do this and also put in place backup management process and fully automate it. Disk space requirements need to be evaluated.Please identify and setup maintenance tasks as required like Rebuild Index, Reorganize index etc….
Database Backup: | Need to configure multiple tempdb database files to avoid drive contention | Done | June-21-2018 |  | Please do this.
Memory Configuration | Configure Max memory and minimum for sql server for better performance. | Done for UAT | June-1-2018 |  | Since appserver and dbserver share the same resources, please find resource needs for both and assign memory as needed so that appserver performance is not impacted.
Locking | Enable lock pages and perform volume maintenance privilege to SQL Server service account. | Done for UAT |  |  | Please do this.
Auto Close | Auto close Database property is enabled for all databases and it not recommended for production databases | Done for UAT | June-1-2018 |  | Please do this.
Standrad maintenance plans | a.Full backup daily 12 am b.transactional log back up -hourly c. Rebuild and Re-organise Index optimization-Weekly d.Integrity Check db daily e.Enable standard trace flags | Done for UAT | June-11-2018
Database Email for notification |  | Done for UAT | June-14-2018
Severity Alerts |  | Done for UAT | June-13-2018